## Aman Alok
Sprint Planning Sheet
Employee Management Service
Task | Priority | Status | Start date | End date | Notes
Eureka-Service | P0 | Completed | 2024-08-21 | 2024-08-21 | Create Eureka Server
Employee-Service | P0 | Completed | 2024-08-21 | 2024-08-22 | Create Employee-service and connect to a DB
Department-Service | P1 | Completed | 2024-08-22 | 2024-08-22 | Create Department table in DB, create a microservice 'Department-Service' and connect to Department table.
Performance-Service | P1 | Completed | 2024-08-23 | 2024-08-27 | Create a microservice to track performance of employee
Task-Service | P1 | Completed | 2024-08-24 | 2024-08-24 | microservice to create task, modify task
API-Gateway-Service | P1 | Completed | 2024-08-25 | 2024-08-26 | Register all microservices to API Gateway service
Authentication-Service | P2 | Completed | 2024-08-27 | 2024-08-30 | apply authentication to employee-service
Junit | P2 | Completed | 2024-08-30 | 2024-08-31 | write test cases for each service
GIT Implementation | P3 | Completed | 2024-09-01 | 2024-09-01 | Submit Source code on Github after completion of project
PPT | P3 | Completed | 2024-09-01 | 2024-09-01 | create ppt for presentation of project
Documentation | P2 | Completed | 2024-08-31 | 2024-09-01 | source code, flow diagrams and pdfs of output to subit on platform in zip

## User
Task | Priority | Status | Start date | End date | Notes
Eureka-Service | P0 | Completed | 2024-08-21 | 2024-08-21 | Create Eureka Server
Employee-Service | P0 | Completed | 2024-08-21 | 2024-08-22 | Create Employee-service and connect to a DB
Department-Service | P1 | Completed | 2024-08-21 | 2024-08-22 | Create Department table in DB, create a microservice 'Department-Service' and connect to Department table.
Performance-Service | P2 | Completed | 2024-08-22 | 2024-08-22 | Create Performance-Service microservice
Task-Service | P2 | Completed | 2024-08-23 | 2024-08-23
API-Gateway-Service | P2 | Completed | 2024-08-24 | 2024-08-25
Authentication-Service | P1 | Completed | 2024-08-24 | 8-24-2024
Junit | P3 | Completed | 2024-08-30 | 2024-08-31
GIT Implementation
PPT